## Sheet1
Initial Product Backlog
Ref | Description | Type | Group | Relative Value | Initial Estimate | Adjust Factor | Estimate | Release | Sprint | Status
1 | As a user, I want to search for train schedules and availability | Feature | Search | 10 | 5 | 1.2 | 6 | MVP | 1 | Ready
2 | As a user, I want to filter search results by departure time, arrival time, train type, etc. | Feature | Search | 8 | 3 | 1.1 | 3.3 | MVP | 1 | In Progress
3 | As a user, I want to view train details such as schedule, route, stops, and fare | Feature | Train Details | 9 | 6 | 1.2 | 7.2 | MVP | 2 | Ready
4 | As a user, I want to reserve a seat on a train and make payment securely | Feature | Booking | 10 | 10 | 1.3 | 13 | MVP | 1 | Ready
5 | As a user, I want to view my booking details and cancel my reservation if necessary | Feature | Booking | 7 | 4 | 1.1 | 4.4 | MVP | 2 | In Progress
6 | As an administrator, I want to manage train schedules, routes, and fare | Feature | Admin | 9 | 12 | 1.4 | 16.8 | Release 1 | 2 | In Progress
7 | As an administrator, I want to view and export sales and booking reports | Feature | Admin | 8 | 8 | 1.3 | 10.4 | Release 2 | 2 | In Progress
8 | As a user, I want to receive email and SMS notifications about my booking status and train delays | Feature | Notifications | 6 | 5 | 1.1 | 5.5 | Release 2 | 1 | Ready
9 | As a user, I want to view train ratings and reviews from other passengers | Feature | Train Details | 5 | 3 | 1.1 | 3.3 | Release 3 | 2 | In Progress
10 | As a user, I'd like to be able to access the website from my mobile as well. | Feature | Search | 9 | 15 | 1.5 | 22.5 | Release 4 | 2 | In Progress