## Sheet1
Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Created | Due | Fix Version/s | Product Backlog
RS-001 | As a scrum master, I want to update the team on the progress | Conducted the daily scrum meeting | Vithyatharshana N | Vithyatharshana N | Present | Done | N/A | Every Monday Starting from 20/03/23 | N/A | Sprint 1 & Sprint 2 | N/A
RS-002 | As a user, I want to login/sign up | Created the login/sign up page and a home page | Thrinayani | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint1 | Creating a page for the user to login or sign up
RS-003 | As a user, I want to reserve a train ticket | Developed the ticket reservation form | Prasoona | Vithyatharshana N | Present | In Progress | N/A | 2023-04-03 | 2023-04-24 | Sprint 2 | Creating a page to book tickets
RS-004 | As a user, I want to order food during my journey/in the station | Developed the form for ordering food | Siri Chandana | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint 1 | Creating a page to order food
RS-005 | As a user, I want to book a coolie | Developed the form for booking a coolie | Mohan | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint 1 | Creating a page to book a coolie
RS-006 | As a user, I want to consult a doctor | Developed the form for health centre booking/ booking a doctor | Prasoona | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint 1 | Creating a page to consult a doctor
RS-007 | As a student, I want to apply for a job here | Developed the form for applying for jobs in various departments | Thrinayani | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint 1 | Creating pages for candidates to apply for a job
RS-008 | As a user, I want to track my train's status | Researched the train tracking API | Siri Chandana | Vithyatharshana N | Present | In Progress | N/A | 2023-04-03 | 2023-04-24 | Sprint 2 | Creating a page to track the train
RS-009 | As a user, I want to cancel my ticket | Adding an option of ticket cancellation on the ticket booking page | Siri Chandana & Prasoona | Vithyatharshana N | Present | In Progress | N/A | 2023-04-03 | 2023-04-24 | Sprint 2 | Adding option of cancelling ticket & Refunding
RS-010 | As a developer, I want to add a payment gateway (including provision of refund when tickets are cancelled) | Integrated the payment gateway API | Mohan | Vithyatharshana N | Present | In Progress | N/A | 2023-04-03 | 2023-04-24 | Sprint 2 | Redirecting the user to a payment page once he/she books a ticket
RS-011 | As a user, I want to give feedback | Development of a feedback form in the Home page | Thrinayani | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint1 | Creating a feedback form on the home page
RS-012 | As a user, I want to contact the management | Adding the contect details on the Home page | Thrinayani | Vithyatharshana N | Present | Done | N/A | 2023-03-20 | 2023-03-27 | Sprint1 | Adding Contact details and social media links on the home page