## Sheet1
Sprint | User Story | Task name | Feature type | Start Date | Finish Date | Duration | Story Points | Status | Release Date | Goal / Objective
1 | As a user, I want to login/sign up | User Authentication | Authentication | 2023-03-20 | 2023-03-27 | 2 hrs | 2 | Done | 2023-03-27 | Enable users to securely login/sign up to the platform
1 | As a user, I want to order food during my journey/in the station | Food Booking | Food Services | 2023-03-20 | 2023-03-27 | 2 hrs | 1 | Done | 2023-03-27 | Allow users to book food during their journey or at the station
1 | As a user, I want to book a coolie | Coolie Booking | Luggage Services | 2023-03-20 | 2023-03-27 | 2 hrs | 2 | Done | 2023-03-27 | Allow users to book a coolie to carry their luggage
1 | As a user, I want to consult a doctor | Doctor Booking | Medical Services | 2023-03-20 | 2023-03-27 | 2 hrs | 2 | Done | 2023-03-27 | Enable users to book a consultation with a doctor/medical staff
1 | As a student, I want to apply for a job here | Job Application | Employment Services | 2023-03-20 | 2023-03-27 | 5 hrs | 2 | Done | 2023-03-27 | Allow students/users to apply for jobs available within the platform
1 | As a user, I want to give feedback | Feedback Submission | Customer Services | 2023-03-20 | 2023-03-27 | 1 hr | 1 | Done | 2023-03-27 | Enable users to submit feedback about their experience
1 | As a user, I want to contact the management | Contact Management | Customer Services | 2023-03-20 | 2023-03-27 | 1 hr | 2 | Done | 2023-03-27 | Allow users to contact the management for any queries or assistance