## Sheet1
Initial Product Backlog
Ref | Description | Type | Group | Relative Value | Initial Estimate | Adjust Factor | Estimate | Release | Sprint | Status
1 | As a user, I want to book a train ticket | Feature | Booking | 10 | 8 | 1.2 | 9.6 | MVP | 2 | Ready
2 | As a user, I want to make a secure payment for my ticket | Feature | Search | 10 | 5 | 1 | 9.6 | MVP | 2 | Ready
3 | As a user, I want to view train details such as schedule, route, stops, and fare | Feature | Train Details | 9 | 5 | 1 | 5 | MVP | 2 | Ready
4 | As a user, I want to view my booking details and cancel my reservation if necessary | Feature | Booking | 8 | 8 | 1.1 | 9.5 | MVP | 2 | Ready
5 | As a developer, I want to integrate the train schedule API | Feature | Search | 8 | 5 | 1 | 5.5 | Relase 2 | 2 | Done
6 | As an administrator, I want to manage train schedules, routes, and fare | Feature | Admin | 10 | 8 | 1.2 | 9.6 | Release 2 | 2 | Ready
7 | As an administrator, I want to maintain a database to manage Contact Us entries | Backend Functionality | Admin | 8 | 5 | 1.2 | 5 | Release 2 | 2 | Done
8 | As an administrator, I want to maintain a database to manage the bookings/feedback (Train Ticket, Doctor, Coolie, Meal, Feedbacks) | Backend Functionality | Admin | 8 | 5 | 1.2 | 5 | Release 2 | 2 | Done