## Sheet1
Sprint | User Story | Task name | Feature type | Start Date | Finish Date | Duration | Story Points | Status | Release Date | Goal / Objective
2 | As a user, I want to book a train | Train Booking | Transportation Services | 2023-04-19 | 2023-04-25 | 3 hrs | 2 | Done | 2023-04-29 | Allow users to book train tickets for their journey
2 | As a user, I want to make payment for the train ticket | Payment Processing | Payment Services | 2023-04-19 | 2023-04-25 | 2 hrs | 3 | Done | 2023-04-29 | Enable users to securely make payments for their train tickets
2 | As a user, I want to track the train's schedule and whereabouts | Train Tracking | Transportation Services | 2023-04-19 | 2023-04-25 | 3 hrs | 3 | Done | 2023-04-29 | Provide users with real-time information about the train's schedule and current location
2 | As an administrator, I want to manage user logins | Manage Users | Admin | 2023-04-20 | 2023-04-25 | 3 hrs | 2 | Done | 2023-04-29 | Manage user logins
2 | As an administrator, I want to manage bookings/feedback (Train Ticket, Coolie, Doctor, Meal, Feedback) | Manage Booking | Admin | 2023-04-20 | 2023-04-25 | 3 hrs | 2 | Done | 2023-04-29 | Manage bookings